## Start Tip4tip React js
Name | Phạm Phú Chinh | [6 empty] | FOR HOUR USE ONLY
Subject | Create a PWA app in React JS with ths following screens | [6 empty] | Hours Worked |  | 28 hour
Dates | From | 2018-11-05 |  | To | 20/05/2018
| Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Total ( hours)
Date | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20
Start | 2018-05-12: 9:00; 2018-05-19: 9:00
End | 2018-05-12: 11:00; 2018-05-19: 11:00
Start | 2018-05-13: 14:00; 2018-05-15: 14:00; 2018-05-20: 14:00
End | 2018-05-13: 15:00; 2018-05-15: 15:00; 2018-05-20: 16:00
Start | 2018-05-12: 15:00; 2018-05-17: 15:00; 2018-05-19: 15:00
End | 2018-05-12: 16:00; 2018-05-17: 17:00; 2018-05-19: 16:00
Start | 20:00 | 21:00 | 19:00 | 20:00 |  | 20:00 |  | 21:00 | 22:00 | 20:00
End | 22:00 | 23:00 | 22:00 | 22:00 |  | 22:00 |  | 22:00 | 12:00 | 22:00
Total | 2:00 | 5:00 | 4:00 | 2:00 | 1:00 | 2:00 | 2:00 | 1:00 | 5:00 | 4:00 | 28:00
| 2 | 5 | 4 | 2 | 1 | 2 | 2 | 1 | 5 | 4 | 28
Job Philippe Required | [10 empty] | Plan time
Create a PWA app in React JS with ths following screens:
| 2018-05-11: Login | 8:00 h
| 2018-05-11: Choose an insurance type (NEXT button) | 4:00 h
| 2018-05-11: Leads Form (SUBMIT button) | 4:00 h
| 2018-05-11: List of my Leads with the status | 4:00 h
Work to do | [10 empty] | Real time | Status
1 | 2018-05-11: Build project ( create the project structure ) | 4:00 h | Done
2 | 2018-05-11: Create "Login" page | 4:00 h | Done
3 | 2018-05-11: Create "Home" page | 5:00 h | Done
4 | 2018-05-11: Create "List of my Leads" page | 3:00 h | Done
5 | 2018-05-11: Create "Choose an insurance type" Page | 3:00 h | Done
6 | 2018-05-11: Create "New Lead" page | 5:00 h | Done
7 | 2018-05-11: Create "Update Lead" page | 4:00 h | Done
Total hours | [10 empty] | 28:00 h

## Change screen item
Name | Phạm Phú Chinh | [6 empty] | FOR HOUR USE ONLY
Subject | Change Screen Item | [6 empty] | Hours Worked
Dates | From | 22/5/2018 |  | To | 27/05/2018
| Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Total ( hours)
Date | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31
Start
End
Start
End
Start
End
Start | 2018-05-22: 20:00; 2018-05-23: 21:00
End | 2018-05-22: 22:00; 2018-05-23: 22:00
Total | 2018-05-22: 2:00; 2018-05-23: 1:00 | 3:00
| 2018-05-22: 2; 2018-05-23: 1 | 3
Job Philippe Required | [10 empty] | Plan time
Create a PWA app in React JS with ths following screens: | [10 empty] | 2 hour
1 | 2018-05-22: Home page : Add a big ADD NEW LEAD button --> the next screen should be choose the insurance type screen
2 | 2018-05-22: Remove CHOOSE INSURANCE from left menu
3 | 2018-05-22: Left menu: when choose Home or Lead, then menu should automatically close after
4 | 2018-05-22: Left menu : Rename LEADS to MY LEADS
5 | 2018-05-22: List of Leads : Rename list of leads to My Leads
6 | 2018-05-22: My Leads: avoid scrolling horizontally --> Move insurance type below Lead Name Remove Tipster columns, reduce date (smaller font or display like: 20-5-2018), Status, keep only View icon (remove Edit icon) | 1 hour
7 | 2018-05-22: Lead detail: add a Edit button on the top right On the Lead Detail Edit : remove "Action" block at the bottom On Lead detail view: rename the bottom bock from "Advanced information" --> "History" and just display the Status History like this: | 2 hour
8 | 2018-05-22: Edit Lead: add a DELETE LEAD red button at the bottom | 1 hour
9 | 2018-05-22: Replace the name app when REACT APP to Tip4tips
Total hours | [10 empty] | 6 hour
Work to do | [10 empty] | Real time | Status
1 | 2018-05-22: Home page : Add a big ADD NEW LEAD button --> the next screen should be choose the insurance type screen | 2 hour | Done
2 | 2018-05-22: Remove CHOOSE INSURANCE from left menu
3 | 2018-05-22: Left menu: when choose Home or Lead, then menu should automatically close after
4 | 2018-05-22: Left menu : Rename LEADS to MY LEADS
5 | 2018-05-22: List of Leads : Rename list of leads to My Leads
6 | 2018-05-22: My Leads: avoid scrolling horizontally --> Move insurance type below Lead Name Remove Tipster columns, reduce date (smaller font or display like: 20-5-2018), Status, keep only View icon (remove Edit icon) | 1 hour | Done
7 | 2018-05-22: Lead detail: add a Edit button on the top right On the Lead Detail Edit : remove "Action" block at the bottom On Lead detail view: rename the bottom bock from "Advanced information" --> "History" and just display the Status History like this: |  | New
8 | 2018-05-22: Edit Lead: add a DELETE LEAD red button at the bottom |  | New
9 | 2018-05-22: Replace the name app when REACT APP to Tip4tips
Total hours | [10 empty] | 3 hour